## Slide 1
MATE ROV COMPETITION · RANGER CLASS
Phase 1 — Foundation
A week-by-week curriculum for parents and stakeholders
Six meetings · mid-June through July 2026 · the road to Dauphin Island begins

## Slide 2
WHY PHASE 1 MATTERS
Six weeks to build a team — not a robot
A new RANGER team will not out-build experienced teams in ten months. But it can out-prepare them on documentation, presentation, and safety — together, forty percent of the total score.
Phase 1 front-loads the things that compound: a real company structure, hands-on skills every kid will use all year, and the habits — notebooks, outreach logs, testing — that turn into points in April.
The SeaMATE Triggerfish kit is the vehicle for the learning. The learning is the deliverable.
40%
of the total score is Engineering & Communication — won by preparation, not parts
6
company roles — every kid an owner with a domain to defend
Week 3
every kid in the water — the milestone new teams quietly miss
02

## Slide 3
PHASE 1 AT A GLANCE
The six-week arc
One meeting a week, two to three hours each. mid-June through July 2026.
1
WEEK 1
Form the Company
Roles, kit, records — and safety culture.
2
WEEK 2
Soldering Bootcamp
Every kid solders. Triggerfish electronics begin.
3
WEEK 3
Electronics & First Splash
Fusing, multimeters — and every kid in the pool.
4
WEEK 4
Build & Iterate
Triggerfish assembled. Capsule leaks diagnosed.
5
WEEK 5
Pilot & Validate
The ROV flies. Capsules pass three dry dives.
6
WEEK 6
Showcase & Launch
Demo day for stakeholders. Phase 2 begins.
PACE At 2-3 hours, Weeks 1 through 4 each run heavy. Each meeting slide carries a pace note — plan to add a meeting on the busiest weeks.
03

## Slide 4
THE COMPANY
Six roles, six owners
MATE structures the competition around a real company. The kids are set — the roles are assigned together in Week 1.
CEO
Schedule, communication with judges and officials, owner of the safety briefing.
CFO
Budget, the bill of materials, and the cost report that judges read.
Mechanical Lead
Frame, buoyancy, the manipulator and payload tools.
Electrical Lead
Power, wiring, fuse selection, and the system interconnect diagram.
Software Lead
Control code, cameras, computer vision — and the team's code repository.
Communications Lead
Outreach log, the build photo log, documentation, and the marketing display.
The pilot is chosen later — and is never the CEO. Stress under the pool lights deserves its own calm operator.
04

## Slide 5
SAFETY
Safety starts on day one
Several safety-inspection findings are automatic fails at the regional. The teams that pass built the habit in June — not in April.
A brief before every session
Each meeting opens with a five-minute safety brief on that day's hazards. By April, the habit is second nature.
The CEO owns it
Safety is a named responsibility, not everyone's vague problem. The CEO runs the brief; the team holds each other to it.
The JSEA habit
Before each new task: what could hurt someone here, and how do we control it? In Phase 5 this becomes the formal Job Safety & Environmental Analysis.
EACH WEEK'S SAFETY FOCUS
WEEK 1
Workspace & hand tools
WEEK 2
Soldering irons & burns
WEEK 3
Electrical, then poolside
WEEK 4
Pool operations & tether
WEEK 5
Pilot rotation & recovery
WEEK 6
Demo day with guests
05

## Slide 6
1
WEEK 1 · SATURDAY, JUNE 13
Form the Company
Focus The team becomes a company — and the kit comes out of the box.
Pace note The densest session of Phase 1. Strongly consider splitting it across two meetings.
WHAT THE KIDS DO
Safety first — set up and label the workspace, and agree the team's shop and tool rules.
Interview for and accept the six company roles — CEO, CFO, and the four leads.
Choose a company name and identity; the Software Lead stands up the GitHub organization (student accounts) and a shared team wiki.
Open and inventory the SeaMATE Triggerfish kit; read the build manual together.
Notebook workshop — how to record a decision with its rationale. Start the outreach log and the build photo log.
THEY LEARN
How a real engineering company is organized — and how to document a decision so it counts in March.
MATERIALS
Triggerfish kit · project notebooks · role cards · outreach + photo log templates · a laptop.
PARENT ROLE
Facilitate the role conversation — don't assign the roles. Confirm pool dates and the transport roster.
BY THE END OF THIS SESSION
A company with six owners, a name, a workspace, and the records that run all year.
06

## Slide 7
2
WEEK 2 · SATURDAY, JUNE 20
Soldering Bootcamp
Focus Every kid solders something — the one non-negotiable Phase 1 outcome.
Pace note Getting six kids to solder well takes time. A second weeknight this week is recommended.
WHAT THE KIDS DO
Open with the soldering safety brief — hot irons, burns, fume ventilation, eye protection.
A 30-minute soldering demo, then hands-on practice joints until each kid is steady.
Begin the Triggerfish electronics — stripping, tinning, heat-shrink, real connections.
Inspect each other's joints: shiny and solid, not cold or bridged.
Notebook and photo log: each kid records and photographs their first solder joints.
THEY LEARN
Soldering, wire stripping, heat-shrink and joint inspection — the foundation electrical skill.
MATERIALS
Two soldering stations · solder & consumables · practice boards · safety glasses · Triggerfish electronics.
PARENT ROLE
Run the 30-minute demo once, then step back. Photograph the build — never hold the iron (MATE Section 4.3).
BY THE END OF THIS SESSION
Six kids who have soldered. The Triggerfish electronics are underway.
07

## Slide 8
3
WEEK 3 · SATURDAY, JUNE 27
Electronics & First Splash
Focus Finish the electronics, learn the multimeter — and get every kid in the water.
Pace note A workshop plus a pool trip in one block. Budget the travel time, or split the pool session out.
WHAT THE KIDS DO
Safety brief — electrical safety and fusing, then the first poolside briefing before anyone enters the water.
Electronics workshop: the multimeter, voltage vs. current, and why a fuse is chosen.
Complete the Triggerfish wiring and topside control box.
Pool session: every kid in the water — comfort, the buddy system, basic familiarity.
First drop test of the waterproofing capsules; open them and check the paper towel.
THEY LEARN
Multimeter measurement, fuse selection and the full-load-amp idea — plus first water time.
MATERIALS
Multimeters · fuses · finished Triggerfish electronics · PVC capsules · the shallow pool.
PARENT ROLE
Arrange lifeguard coverage and confirm every kid's swim ability. Lock the deep-water host for the year.
BY THE END OF THIS SESSION
Milestone — every kid in a pool by Week 3. The Triggerfish electronics are done.
08

## Slide 9
4
WEEK 4 · SATURDAY, JULY 11
Build & Iterate
Focus The Triggerfish comes together; the waterproofing exercise gets serious.
Pace note A full build plus a pool test. Tight at 2-3 hours — protect the time, or add a session.
WHAT THE KIDS DO
Poolside safety brief — tether handling, deck discipline, electricity near water.
Assemble the Triggerfish frame, thrusters and tether — the first full build.
Pool: capsule dive #2 — open every capsule, check the towel, diagnose each leak.
Redesign and re-seal the capsules that failed; iterate the O-ring and penetration.
Notebook and photo log: record what leaked, why, and the fix that was tried.
THEY LEARN
Mechanical assembly, and waterproofing through O-rings, epoxy and a single clean penetration.
MATERIALS
Triggerfish frame & thrusters · PVC capsules · epoxy · O-rings · the shallow pool.
PARENT ROLE
Ask "what would you change?" — don't fix it for them. Let the leaks happen; the recovery is the lesson.
BY THE END OF THIS SESSION
The Triggerfish is assembled. Capsule designs improve dive over dive.
09

## Slide 10
5
WEEK 5 · SATURDAY, JULY 18
Pilot & Validate
Focus Fly the Triggerfish — and prove the capsules stay dry.
Pace note More manageable — piloting and capsule validation share one pool block.
WHAT THE KIDS DO
Poolside safety brief — pilot rotation, the buddy system, and safe capsule recovery.
Pool session: every kid pilots the Triggerfish; tune buoyancy and trim.
Capsule dive #3 — the target is three consecutive dry dives.
Notebook and photo log: document exactly what made a seal hold.
Capture the story moments — what broke this month and how the team recovered.
THEY LEARN
Piloting and trim — and closing out an engineering test with real evidence.
MATERIALS
Completed Triggerfish · capsules · project notebooks · the shallow pool.
PARENT ROLE
Observe and time the runs. Record the failure-and-recovery stories — those win the April Q&A.
BY THE END OF THIS SESSION
A flying starter ROV. The capsule exercise on track — the Phase 2 float skill is proven.
10

## Slide 11
6
WEEK 6 · SATURDAY, JULY 25
Showcase & Launch Phase 2
Focus Show the work, close Phase 1, and set up the fall.
Pace note A lighter session by design — demo, reflect, and look ahead.
WHAT THE KIDS DO
Safety brief for demo day — running the pool with an audience and guests on the deck.
Final Triggerfish pool demonstration for parents and stakeholders.
Role retrospective — what each lead learned; review the notebook, outreach and photo logs.
Preview Phase 2: sub-team mini-projects, the float v1, the school-year cadence.
Thank-yous to everyone who hosted, donated, or volunteered — logged as outreach.
THEY LEARN
Presenting their own work to an audience — and reflecting honestly as a team.
MATERIALS
Triggerfish · the notebook, outreach and photo logs · the Phase 2 overview.
PARENT ROLE
Invite stakeholders and potential sponsors to the showcase. Celebrate what six weeks built.
BY THE END OF THIS SESSION
Milestone — starter ROV in the water, company formed, deep-pool confirmed. Phase 1 complete.
11

## Slide 12
RUNNING UNDERNEATH ALL SIX MEETINGS
Three threads that never get their own session
They run quietly through every meeting — and each one turns directly into points in the spring.
STARTED WEEK 1
Notebook & photo log
Every kid records decisions with their rationale; the Communications Lead keeps a running photo log of the build. In March both feed the technical documentation.
STARTED WEEK 1
Community-outreach log
Every volunteer and outreach hour is logged from day one. In April it converts directly into Corporate Responsibility points.
WEEKS 1 THROUGH 5
Waterproofing capsule
Designed Week 1, built Week 2, tested and re-sealed Weeks 3-5. The gate is three consecutive dry dives — the foundation skill for the Phase 2 float.
12

## Slide 13
WHAT WE NEED FROM PARENTS
The parent side of Phase 1
BEFORE WEEK 1
Order the Triggerfish kit and tools now — SeaMATE lead times run two weeks or more.
Confirm the deep-water pool host for the year.
Build the weekly transport roster and lock a consistent meeting day and time.
EVERY WEEK, ALL SEASON
Photograph the build — never hold the iron (MATE Section 4.3).
Teach a skill once, then step back and let them fail.
Order parts, manage budget, coordinate logistics — program management, not engineering.
OPEN ITEM The deep-water pool host is not yet confirmed. Locking it is the single most important parent task before the season's float work begins.
The rule for the year: teach a skill once, then step back and let them fail. The kids learning to recover from failure is what makes the engineering-presentation Q&A go well in April.
13

## Slide 14
PHASE 1 BUDGET
What it costs to start
SeaMATE Triggerfish ROV kit
$950
Two soldering stations and consumables
$130
Two multimeters and hand tools
$110
Waterproofing capsule exercise — PVC, end caps, O-rings, epoxy
$50
Phase 1 total
$1,240
OF A $4,400 SEASON
28%
Phase 1 is the largest single-phase spend of the year — it buys the kit and tools every later phase builds on.
Excludes pool access (donated) and project notebooks (kids bring their own).
14

## Slide 15
WHAT SUCCESS LOOKS LIKE
By the end of July
✓
A company that exists Six roles, six owners, a name, and a safety culture.
✓
Six kids who have soldered And who have all been in the water by Week 3.
✓
A starter ROV, flying The SeaMATE Triggerfish, built and piloted by the team.
✓
Pool access locked For the full year — including the deep-water host.
“If we do nothing else in June: buy the kit, get six kids soldering, and put it in the water within three weeks. Everything else in this plan is downstream of that.”